## Sheet1
Capstone 1 - Capstone Project Boostrap
Nhóm | Thành viên 1 |  |  |  | Thành viên 2 |  |  |  | Project
6 | Lê Quang Nhật (Dev 1) |  |  |  | Phan Thị Huyền Trang (Dev 2) |  |  |  | 1
| + Link github: https://github.com/LeeQuangNhat/BC61-Capstone-MasterWork.git + Link youtube: https://youtu.be/G1iRL6IaiN4 + Link vercel: https://bc-61-capstone-master-work.vercel.app/ |  |  |  | + Link github: https://github.com/LeeQuangNhat/BC61-Capstone-MasterWork.git + Link youtube: + Link vercel: https://bc-61-capstone-master-work.vercel.app/
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 11/12/2023 | 25/12/2023 | 100% | Dev 1 | 11/12/2023 | 25/12/2023 | 100% | Dev 2
Footer | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
Home | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
Landing page | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
Contact | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
Dark mode | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
About | 11/12/2023 | 25/12/2023 |  | Dev 2 | 11/12/2023 | 25/12/2023 |  | Dev 1
Services | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023
404 not found | 11/12/2023 | 25/12/2023 |  |  | 11/12/2023 | 25/12/2023